## Title Page
Submitted: 3/11/2019
Approved: 3/11/2019
| First Name | Last Name | Office/Title | Phone Number | E-mail
Alternate Contact | Pamela | Main | DOE Office of the CIO | 301-903-4261 | Pamela.main@hq.doe.gov
Responsible Officer | Steven | Golisch | DOE Bonneville Power Administration Telecommunications Design Group | 360-619-6561 | scgolisch@bpa.gov
Primary Contact | George | Dudley | DOE Office of the CIO | 202-586-6730 | george.dudley@hq.doe.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Alternate Frequency Assignment | Geographic Location associated with Timeline | Sharing Type | Indefinite Sharing Timeline (Months after 1/30/15) | Temporary Sharing Timeline (Months after 1/30/15) | Vacate Assignment Timeline (Months after 1/30/15)
DOE786122 | T | 1765 |  | 8 | 2 | Microwave | Microwave Link | OR | 453423N | 1224727W | WA | 453905N | 1224339W | TBD | EA 167 | None |  |  | 30
DOE924929 | 3A | 1765 |  | 10 | 2 | Microwave | Microwave Link | OR | 454041N | 1204410W | WA | 454345N | 1204224W | TBD | EA 167 | None |  |  | 30
DOE945250 | 4K-1 | 1757.5 |  | 0.8 | 2 | Microwave | Microwave Link | OR | 434625N | 1201654W | OR | 434841N | 1205229W | TBD | EA 167 | None |  |  | 30
DOE945254 | 4K-2 | 1767.5 |  | 0.8 | 2 | Microwave | Microwave Link | OR | 433034N | 1190725W | OR | 433332N | 1190909W | TBD | EA 150 | None |  |  | 30
DOE955040 | 13A | 1777.5 |  | 0.8 | 2 | Microwave | Microwave Link | WA | 461351N | 1190234W | WA | 461543N | 1191722W | 4 GHz | EA 169 | None |  |  | 30
DOE955303 | 3K | 1767.5 |  | 1 | 2 | Microwave | Microwave Link | CA | 412458N | 1210632W | CA | 413050N | 1203813W | 7-8 GHz | EA 165 | None |  |  | 30
DOE984990 | 3D | 1775 |  | 1 | 2 | Microwave | Microwave Link | WA | 471909N | 1201423W | WA | 470618N | 1193144W | TBD | EA 169 | None |  |  | 30

## Funds
System Name | Total Pre-Auction Cost ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Cost Pre-2012 ($M) | Equipment Cost ($M) | Deployment Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months) | End Expenditure Timeline (Months) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
13A | 0 | 0 | 0 | 0.42 | 1.98 | 2.4 | 1 | 62 | 0.02 | Expand channel capacity to 16 DS1 | Expanded channel capacity to 16 each DS1 will provide sufficient capacity to meet existing telecommunication circuit needs including Teleprotection, SCADA, Telemetering, Site Security, Voice, IT and future Smart Grid applications to control and operate the power transmission grid per Western Electric Coordinating Council (WECC) and North America Electric Reliability Council -Critical Infastructure Protection (NERC-CIP) requirements. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
3A | 0 | 0 | 0 | 0.05 | 0.05 | 0.1 | 1 | 62 |  |  | BPA will temporarly relocate the existing frequency assignments from the 1755-1780 MHz band to the 1780-1850 MHz band. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
3D | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | BPA is funding the relocation of this microwave point-to-point path with a new digital microwave or fiber technology. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
3K | 0 | 0 | 0 | 0.42 | 1.98 | 2.4 | 1 | 62 | 0.02 | Expand channel capacity to 16 DSI | Expanded channel capacity to 16 each DS1 will provide sufficient capacity to meet existing telecommunication circuit needs including Teleprotection, SCADA, Telemetering, Site Security, Voice, IT and future Smart Grid applications to control and operate the power transmission grid per Western Electric Coordinating Council (WECC) and North America Electric Reliability Council -Critical Infastructure Protection (NERC-CIP) requirements. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
4K-1 | 0 | 0 | 0 | 0.05 | 0.05 | 0.1 | 1 | 62 |  |  | BPA will temporarly relocate the existing frequency assignments from the 1755-1780 MHz band to the 1780-1850 MHz band. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
4K-2 | 0 | 0 | 0 | 0.05 | 0.05 | 0.1 | 1 | 62 |  |  | BPA will temporary relocate the existing frequency assignments from the 1755-1780 MHz band to the 1780-1850 MHz band. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
Headquarters Overhead | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 1 | 62 |  |  | Costs required for oversight and program management at Headquarters DOE. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
T | 0 | 0 | 0 | 0.05 | 0.05 | 0.1 | 1 | 62 |  |  | BPA will temporary relocate the existing frequency assignments from the 1755-1780 MHz band to the 1780-1850 MHz band. March 11, 2019: AWS-3 SRF funds will need to be retained by BPA for over five years after BPA first received AWS-3 funds, at least through FY 2020 (a total of 62 months since receiving SRF funds in July 2015) in order to perform reliability testing, modification to electricity power supply hookups, and to complete the construction of two communications buildings. Those efforts will assure “comparable capability” has been achieved.
Total | 0 | 0 | 0 | 1.04 | 5.76 | 6.8 |  |  | 0.04

## Interactions
Interaction Name | Interaction Description
1. Alternate Bands | BPA will be seeking permanent frequency assignments in the 4 GHz and 8 GHz band in order to move out of the 1755-1780 MHz spectrum. Thus, the need to receive the 4 GHz and 8 GHz frequency assignments in a timely manner.
2. Freq Assignments | BPA will be seeking temporary frequency assignments in the 1780-1850 MHz band in order to move out of the 1755-1780 MHz spectrum. Thus, the need to receive the 1780-1850 MHz frequency assignments in a timely manner.
3. Weather Complications | The relocation effort for all sites listed for vacating are subject to extreme weather conditions during winter months which can delay the deployment of new equipment installation including towers, antenna and RF microwave radio systems.

## Impact Factors
Factor Name | Factor Description
Freq Assignments | NTIA will need to work closely with the Federal frequency assignment incumbents to determine new frequency assignments in the alternate bands including the 1780-1850 MHz, 4 GHz and 7/8 GHz bands for point-to-point microwave.

## Notes
Note Name | Note Text
1. Note 1 | BPA will temporarly relocate the existing frequency assignments from the 1755-1780 MHz band to the 1780-1850 MHz band.
2. Note 2 | DOE 955040 (Paired with DOE 955039) and DOE 955303 (Paired with DOE 955305): Cost funding listed for frequency assignment pair covers total point-to-point microwave replacement cost.
3. Note 3 | All other assignments: BPA is funding the relocation of this microwave point-to-point path with a new digital microwave or fiber technology.
4. Paired Serial Numbers | [Serial Number - Center Freq./Paired RX Serial Number -Paired RX Frequency (RX State)] [DOE 786122 - M1765 / DOE 786123 - M1825 (WA)] [DOE 924929 - M1765 / DOE 786106 - M1825 (WA)] [DOE 945250 - M1757.5 / DOE 945249 - M1817.5 (OR)] [DOE 945254 - M1767.5 / DOE 945253 - M1827.5 (OR)] [DOE 955040 - M1777.5 / DOE 955039 - M1837.5 (WA)] [DOE 955303 - M1767.5 / DOE 955305 - M1827.5 (CA)] [DOE 984990 - M1775 / DOE 984991 - M1835 (WA)]
Revision of timeline completion to FY20 | BPA requires an extension of its original completion timeline of 30 and 48 months respectively out to 62 months for its 7 systems. BPA anticipates completing all AWS-3 transition work by September 30, 2020. Reasoning why AWS-3 SRF funds need to be retained by BPA over its original timeline is in order to perform reliability testing, modification to its electricity power supply hookups, and to complete the construction of two communications buildings for Systems 3-K and 13-A. These efforts will assure “comparable capability” has been achieved. BPA has been off all AWS-3 assignments since July, 2018.

## Excluded Info
Table | Row | Column | Agency Marking | Reference