## Title Page
Submitted:
Approved:
| First Name | Last Name | Office/Title | Phone Number | E-mail
Responsible Officer | Christina | McCann | Treasury Inspector General for Tax Administration(TIGTA) | 301-210-8729 | Christina.McCann@tigta.treas.gov
Primary Contact | Christina | McCann | Treasury Inspector General for Tax Administration (TIGTA) | 301-210-8729 | Christina.McCann@tigta.treas.gov
Alternate Contact | Russell | Lovell | Internal Revenue Service- Criminal Investigation | 510-715-9087 | Russell.Lovell@ci.irs.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth (MHz) | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Frequency Remarks | Geographic Location associated with Timeline (AAO in this column indicates the timeline is associated with the geographic location defined by the Authorized Area of Operation in the frequency assignment) | Sharing Type (Indefinite, Temporary i.e. Coordinated, or None) | Temporary Sharing Timeline (Months After 1/31/2015) | Indefinite Sharing Timeline (Months After 1/31/2015) | Vacate Assignment Timeline (Months After 1/31/2015)
T020185 | TIGTA Techops | 1765 |  | 6 | 6 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | USP | None |  |  | 12
T060040 | CI Techops | 1760 |  | 6 | 6 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | USP | None |  |  | 12

## Funds
System Name | Total Pre-Auction Cost ($M) | Funds Requested Prior to Auction ($M) | Pre-Auction Cost Pre-2012 ($M) | Transition Implementation Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months after Receipt of Funds) | End Expenditure Timeline (Months after Receipt of Funds) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
CI Techops | 0 | 0 | 0 | 7.561 | 7.561 | 6 | 74 |  | Requesting 14 month extension for CI Techops (revised timeline to 74 months) or by 09/2021 | Funds required to replace antiquated, analog equipment. The equipment is channelized so is still useable. However, the loss of one frequency cuts down the number of available channels by 33% (1 of 3 available) which diminishes efforts to avoid interference in this very congested band. Procurement of spectrally efficient COFDM equipment will help avoid interference when encountered.
TIGTA Techops | 0 | 0 | 0 | 0.241 | 0.241 | 6 | 77 |  | Requesting 10 month extension for TIGTA Ops (revised timeline to 77 months) or by 12/2021. See Rev 6 under NOTES. | Procurement of replacement digital COFDM microwave equipment and IP-based systems which are more spectrally efficient than the current wideband analog equipment.
Total

## Interactions
Interaction Name | Interaction Description
1 | In order to execute this plan, it is necessary for NTIA to assign fequencies to IRS-CI in the 2.2 to 2.29 GHz range. IRS-CI currently does not have any frequencies in the S band. IRS-CI will be transistioning its existing L band equipment into more spectrally efficient digital COFDM frequencies in the S Band. Commercial services may no longer be a viable option for most operations due to the removal of the unlimited data plans for federal users. Commercial services may continue to be used on a limited basis for very short-term operations. The majority of the transition plan will rely on vacating the L band and switching to the S Band.

## Impact Factors
Factor Name | Factor Description
1-Obtainning Replacment Frequencies | Additional frequencies are requested in the S Band (2.2-2.29 GHz) to replace the loss of these frequencies.
2- Availablity of Equipment | Potential Delays could occur if there was a lack of available replacement equipment.

## Notes
Note Name | Note Text
Comparable Capability | Although both TIGTA and IRS – CI believe they will be able to vacate the affected frequencies within 12 months of receipt of funding, they both believe it will take up to 5 years (60 months) to reach comparable capability. The reason for this extended time is because the small disguised video transmitter equipment is currently not available and to allow for futher advancement in the microwave arena.
Rev. 5 Changes | CI Techops operations requesting a 14 month extension from 60 months or by 07/2020 to 74 months or by 09/2021. Treasury’s Counter Intelligence operators have utilized $3 million of the ~$4.7 million remaining during FY20, but due to the current pandemic and an agency reorganization, project completion and procurement efforts have been delayed. Extension will allow CI time to appropriately close out program efforts. TIGTA Techops, requesting a 7 month extension from 60 months or by 07/2020 to 67 months or by 02/2021. The Department of the Treasury is working to close out and utilizing the remainder of funds available, but due to the pandemic, service requests have been delayed. To allow for sufficient time to close out contracts, an extension until 2/2021, has been requested.
Rev. 7 Changes | TIGTA Techops requesting a 10 month extension from 67 months or by 02/2021 to 77 months or by 12/2021. The Department of the Treasury is working to close out and utilizing the remainder of funds available and has decreased funds considerably in 2020, but due to the pandemic and moving one contract to be funded differently, exhaustion has been delayed. To allow for sufficient time to execute a final contract, an extension until 12/2021 has been requested.

## Excluded Info
Table | Row | Column | CUI Category | Safeguarding and/or Dissemination Authority