## Title Page
Submitted: 7/3/2014
Approved: 10/28/2015
| First Name | Last Name | Office/Title | Phone Number | E-mail
Primary Contact | Michael | Mirando | VA OI&T EIE | 202-461-5307 | Michael.Mirando@va.gov
Responsible Officer | Ryan | Gholson | Department of Veterans Affairs, Office of Inspector General | 601-364-7285 | ryan.gholson@va.gov
Alternate Contact | Don | Bronson | VA OI&T EIE | 202-461-5301 | Don.Bronson@va.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Alternate Frequency Assignment | Geographic Location associated with Timeline | Sharing Type | Indefinite Sharing Timeline (Months after 1/30/15) | Temporary Sharing Timeline (Months after 1/30/15) | Vacate Assignment Timeline (Months after 1/30/15)
VA020123 | OIG VS | 1770 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | South East FO Region | None |  |  | 15
VA020123 | OIG VS | 1770 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Central FO Region | None |  |  | 15
VA020123 | OIG VS | 1770 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Northwest FO Region | None |  |  | 15
VA020123 | OIG VS | 1770 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Mid-Atlantic FO Region | None |  |  | 15
VA020123 | OIG VS | 1770 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | South Central FO Region | None |  |  | 15
VA020123 | OIG VS | 1770 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Northeast FO Region | None |  |  | 15
VA020123 | OIG VS | 1770 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Western FO Region | None |  |  | 15
VA020269 | OIG VS | 1775 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Mid-Atlantic FO Region | None |  |  | 15
VA020269 | OIG VS | 1775 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Western FO Region | None |  |  | 15
VA020269 | OIG VS | 1775 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | South Central FO Region | None |  |  | 15
VA020269 | OIG VS | 1775 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Northwest FO Region | None |  |  | 15
VA020269 | OIG VS | 1775 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Northeast FO Region | None |  |  | 15
VA020269 | OIG VS | 1775 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | South East FO Region | None |  |  | 15
VA020269 | OIG VS | 1775 |  | 17 | 8 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | Central FO Region | None |  |  | 15

## Funds
System Name | Total Pre-Auction Cost ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Cost Pre-2012 ($M) | Equipment Cost ($M) | Deployment Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months) | End Expenditure Timeline (Months) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
OIG VS | 0 | 0 | 0 | 0.275 | 0 | 0.275 | 0 | 12 |  |  | Replacement cost for 25 video systems @ $11,000 each.
Total | 0 | 0 | 0 | 0.275 | 0 | 0.275 |  |  | 0

## Interactions
Interaction Name | Interaction Description
1. Receipt of Funds. | Transition timelines are dependent on receipt of funds by May 2015. Receipt of funds earlier or later will adjust the vacate dates accordingly.

## Impact Factors
Factor Name | Factor Description
1 | New USP assignments in the alternate band must be approved by NTIA by 2/28/2015. See Notes Tab for optional alternate bands.

## Notes
Note Name | Note Text
1 | This transition plan identifies the funds required to replace video surveillance systems used during investigations by the Department of Veterans Affairs Office of Inspector General (OIG) in support of making the 1755-1780 MHz band available for auction.
2 | The VA OIG is currently divided into 7 regions throughout the Continental United States. Each region has a field office and several smaller resident agency offices (sub-offices) fall under the direction and control of the regions field office. All the equipment is located at the main office. When the main field office is transitioned over to the new spectrum, all the resident agencies are transferred as well because they utilize the equipment housed in the main field office.
3 | The regions will be transitioned in the following priority order: [1] Northeast FO Region: NY, NJ, DE, CT, RI, MA, NH, ME, VT, Eastern PA; [2] Western FO Region: AZ, NM, UT, Southern NV, Southern CA; [3] Central FO Region: IN, IL, MI, WI, MO, IA, NE, KS, CO, WY, ND, MN, SD, OH; [4] South Central FO Region: TX, OK, AR, LA, MS; [5] South East FO Region: GA, AL, TN, KY, FL, PR; [6] Northwest FO Region: WA, OR, AK, MT, ID, Northern NV, Northern CA, Eastern CA, HI, Philippines, Guam; and [7] Mid-Atlantic FO Region: DC, MD, VA, Southern WV, SC, NC, Western PA, Northern WV
4 | The alternate radio frequency assignments for the new assignment must be in one of the following bands. [1] C: 4400-5000 MHz [2] L: 1710-1850 MHz [3] S2/3: 2200-2400 MHzMHz (specifically request 2200-2290 MHz)

## Excluded Info
Table | Row | Column | Agency Marking | Reference