## Title Page
Submitted: 9/19/2022
Approved: 9/19/2022
| First Name | Last Name | Office/Title | Phone Number | E-mail
Alternate Contact | John | Whitlowe | DOI/Office of the Chief Information Officer | 703-648-5549 | John_Whitlowe@ios.doi.gov
Responsible Officer | Steven | Goodson | DOI/Office of the Chief Information Officer | 703-648-5595 | steven_goodson@ios.doi.gov
Primary Contact | Steven | Goodson | DOI/Office of the Chief Information Officer | 703-648-5595 | steven_goodson@ios.doi.gov
Note: In order to receive SRF funding for efforts prior to the auction, this federal entity has agreed that it will provide (I) to the fullest extent possible, for sharing and coordination of eligible frequencies with non-Federal users, including reasonable accommodation by the eligible Federal entity for the use of eligible frequencies by non-Federal users during the period that the entity is relocating its spectrum uses (in this clause referred to as the ‘‘transition period’’); and (II) for non-Federal users to be able to use eligible frequencies during the transition period in geographic areas where the eligible Federal entity does not use such frequencies. Additionally, this eligible Federal entity will, during the transition period, make itself available for negotiation and discussion with non-Federal users not later than 30 days after a written request therefor; and during the transition period, make available to a non-Federal user with appropriate security clearances any classified information (as defined in section 798(b) of title 18) regarding the relocation process, on a need-to-know basis, to assist the non-Federal user in the relocation process with such eligible Federal entity or other eligible Federal entities. [47 U.S.C. § 928(d)(3)(B)(ii)]

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth (MHz) | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Frequency Remarks | Geographic Location associated with Timeline (AAO in this column indicates the timeline is associated with the geographic location defined by the Authorized Area of Operation in the frequency assignment) | Sharing Type (Indefinite, Temporary i.e. Coordinated, or None) | Temporary Sharing Timeline (Months After 1/31/2015) | Indefinite Sharing Timeline (Months After 1/31/2015) | Vacate Assignment Timeline (Months After 1/31/2015)
C050522-DOI-11 | Boise, ID - GOES (RRC BORPNRHA) | 1694.5 |  | 4 | 2.2 | MetSat | ID Boise | SPC | xxxxxxx | xxxxxxxx | ID | 433653N | 1161508W | N/A | ID Boise | Indefinite |  | 39
C050522-DOI-13 | Guaynabo, PR - GOES (RRC CWSC) | 1694.5 |  | 4 | 2.2 | MetSat | PR Guaynabo | SPC |  |  | PR | 182526N | 0660650W | N/A | PR Guaynabo | Indefinite |  | 39
C050522-DOI-15 | Knoxville, TN - GOES (RRC TVARFC) | 1694.5 |  | 4 | 2.2 | MetSat | TN Knoxville | SPC |  |  | TN | 355758N | 0835513W | N/A | TN Knoxville | Indefinite |  | 39
C050522-DOI-5 | Sioux Falls, SD - GOES (RRC EDDN-1) | 1694.5 |  | 4 | 2.2 | MetSat | SD Sioux Falls | SPC |  |  | SD | 434406N | 0963732W | N/A | SD Sioux Falls | Indefinite |  | 39
C050523-DOI-10 | Boise, ID - GOES (RRC BORPNRHA) | 1694.8 |  | 4 | 2.2 | MetSat | ID Boise | SPC |  |  | ID | 433653N | 1161508W | N/A | ID Boise | Indefinite |  | 39
C050523-DOI-12 | Guaynabo, PR - GOES (RRC CWSC) | 1694.8 |  | 4 | 2.2 | MetSat | PR Guaynabo | SPC |  |  | PR | 182526N | 0660650W | N/A | PR Guaynabo | Indefinite |  | 39
C050523-DOI-14 | Knoxville, TN - GOES (RRC TVARFC) | 1694.8 |  | 4 | 2.2 | MetSat | TN Knoxville | SPC |  |  | TN | 355758N | 0835513W | N/A | TN Knoxville | Indefinite |  | 39
C050523-DOI-4 | Sioux Falls, SD - GOES (RRC EDDN-1) | 1694.8 |  | 4 | 2.2 | MetSat | SD Sioux Falls | SPC |  |  | SD | 434406N | 0963732W | N/A | SD Sioux Falls | Indefinite |  | 39
C050542-DOI-7 | Sioux Falls, SD - GOES (RRC EDDN-2) | 1694.5 |  | 4 | 2.2 | MetSat | SD Sioux Falls | SPC |  |  | SD | 434418N | 0963737W | N/A | SD Sioux Falls | Indefinite |  | 39
C050542-DOI-9 | Boise, ID - GOES (RRC NFIC) | 1694.5 |  | 4 | 2.2 | MetSat | ID Boise | SPC |  |  | ID | 433403N | 1161240W | N/A | ID Boise | Indefinite |  | 39
C050543-DOI-6 | Sioux Falls, SD - GOES (RRC EDDN-2) | 1694.8 |  | 4 | 2.2 | MetSat | SD Sioux Falls | SPC |  |  | SD | 434418N | 0963737W | N/A | SD Sioux Falls | Indefinite |  | 39
C050543-DOI-8 | Boise, ID - GOES (RRC NFIC) | 1694.8 |  | 4 | 2.2 | MetSat | ID Boise | SPC |  |  | ID | 433403N | 1161240W | N/A | ID Boise | Indefinite |  | 39
C860054-DOI-3 | Sioux Falls, SD - POES (RRC EROSLRPS) | 1698 |  | 1.328 | 1.328 | MetSat | SD Sioux Falls | SPC | xxxxxxx | xxxxxxxx | SD | 433409N | 0963733W | N/A | SD Sioux Falls | Indefinite |  | 39
C860055-DOI-1 | Sioux Falls, SD - POES (RRC EROSLRPS) | 1702.5 |  | 1.328 | 1.328 | MetSat | SD Sioux Falls | SPC | xxxxxxx | xxxxxxxx | SD | 433409N | 0963733W | N/A | SD Sioux Falls | Indefinite |  | 39
C860056-DOI-2 | Sioux Falls, SD - POES (RRC EROSLRPS) | 1707 |  | 1.328 | 1.328 | MetSat | SD Sioux Falls | SPC | xxxxxxx | xxxxxxxx | SD | 433409N | 0963733W | N/A | SD Sioux Falls | Indefinite |  | 39

## Funds
System Name | Total Pre-Auction Cost ($M) | Funds Requested Prior to Auction ($M) | Pre-Auction Cost Pre-2012 ($M) | Transition Implementation Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months after Receipt of Funds) | End Expenditure Timeline (Months after Receipt of Funds) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
Boise, ID - GOES (RRC BORPNRHA) | 0.031 | 0.019 | 0.012 | 12.969 | 13 | 1 | 144 |  |  | Boise sites are not co-located.
Boise, ID - GOES (RRC NFIC) | 0.031 | 0.019 | 0.012 | 12.969 | 13 | 1 | 144 |  |  | Boise sites are not co-located.
Guaynabo, PR - GOES (RRC CWSC) | 0.031 | 0.019 | 0.012 | 8.158 | 8.189 | 1 | 75 |  |  | Decommission
Knoxville, TN - GOES (RRC TVARFC) | 0.031 | 0.019 | 0.012 | 12.921 | 12.952 | 1 | 144
Sioux Falls, SD - GOES (RRC EDDN-1) | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Sites colocated -- Costs included under RRC EROSLRPS
Sioux Falls, SD - GOES (RRC EDDN-2) | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Sites colocated -- Costs included under RRC EROSLRPS
Sioux Falls, SD - POES (RRC EROSLRPS) | 0.031 | 0.019 | 0.012 | 17.633 | 17.664 | 1 | 144
Total | 0.155 | 0.095 | 0.06 | 64.65 | 64.805 |  |  | 0

## Interactions
Interaction Name | Interaction Description
1. ITS Coordination Portal | Engage ITS Boulder to setup sharing coordination portal
2. Interference Mitigation | Faciliate enforcement should interference above allowable levels occur at MetSat downlink sites discovered during monitoring.
3. Coordination Procedures | Facilitate coordination with FCC in developing initial coordination agreements and dealing with enforcement issues relative to band sharing arrangements

## Impact Factors
Factor Name | Factor Description
1. Technology/Development | Adequate and proper phasing of funds will be required to enable development of capabilities necessary to allow sharing of spectrum in accordance with legislation.
2. Frequency Sharing Coordination | Ability to validate entities' methodologies for sharing.
3. Regulatory Criteria | Regulatory criteria will provide private sector user incentive to not interfere with Federal stations without jeopardizing DOI/TVA ability to complete the mission and/or execute its primary mission essential functions.
4. Incumbent Support | Incumbents will support interference testing to determine feasibility of co-existence and necessary equipment alterations, and they will support the relocation plan and equipment deployment as necessary to address interference issues.

## Notes
Note Name | Note Text
Additional Funding and Expenditure timeline Extension | OMB authorized additional AWS 3 funding in the amount of $30,476,867. New approved expenditure’s funding timeline extension is June 30, 2027.
Executive Summary | This transition plan identifies all the required actions and costs needed to make the 1695-1710 MHz band available for auction for shared use with wireless broadband providers. In the establishment of protection distances around critical DOI and TVA MetSat locations used to receive environmental sensor data, DOI plans to install monitoring capabilities at each of the receiver locations to ensure compliance with the interference threshold criteria established by the FCC and to provide the ability to identify and mitigate any interference experienced from the wireless broadband providers in the shared band. This plan includes 3 years of Operations and Maintenance (O&M) after the monitoring is deployed and supports cost sharing for the compliance monitoring development by DOC/NOAA. DOI also supports and is planning on the establishment of a spectrum coordination portal developed by ITS-Boulder. This portal development is in conjunction with the DOC/NOAA and DOD to facilitate the successful coordination between the AWS licensees and federal agencies of sharing arrangements now and into the future. This plan includes costs for a cost-sharing of the total cost for the portal development and 3 years of O&M.
Extension of Expenditures Request | DOI is requesting a 15 month extension (from 75 months to 90 months) for expenditure of fund to offset the delay in awarding of the RFIMS contract.

## Excluded Info
Table | Row | Column | CUI Category | Safeguarding and/or Dissemination Authority