## A. Title Page
Department of Transportation (DOT) FAA Transition Plan for the 1755-1780 MHz Band
| Primary Point of Contact: Ian Atkins Office: Office of Radio Frequency Management Telephone Number: 202-267-7531 E-mail: ian.atkins@faa.gov |  | Alternate Point of Contact: Margarette Ebate Office: Office of Radio Spectrum Management Telephone Number: 202-493-5195 E-mail: margarette.ebate@faa.gov
Certification regarding Classified and Sensitive Information: I, Ian Atkins, certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information.

## B. General Information
Department of Transportation (DOT) Transition Plan for 1755-1780 MHz Band Tab B: General Information
| This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs: | 0 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 0
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 0
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | No
4 | a. Name of Responsible Officer: | Ian Atkins
b. (Optional) Office:
c. (Optional) Telephone Number:
d. (Optional) E-mail:
5 | Total Transition Plan Cost ($M): | 0.43326

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment | Transition Timeline (Months)
FAA 922573 | 1765 |  | 3 | 70 |  | Microwave | Elwood ARSR - New Lenox RCO LOW DENSITY RCLT DIGITAL 2 GHZ 97-600 VDM CHANNELS | FAA Great Lakes | IL | 41-25-22.00 N | 88-03-30.00 W | IL | 41-32-53.99 N | 87-56-53.20 W | Vacate with Temp | Commercial | 12

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
FAA 922573 | FAAGreat Lakes | 6 months |  | 12 months

## E. Timeline for Funds
System Name | System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
Elwood ARSR - New Lenox RCO LOW DENSITY RCLT DIGITAL 2 GHZ 97-600 VDM CHANNELS | 245KJB | 0 | 0 | 0 | 0.18326 | 0.25 | 0.43326 | 3 | 60 | 0 |  | Replace FAA-owned 2GHz LDRCL with FTI-commercial Last Mile Microwave

## F. NTIA Interactions
1 | Interaction required with NTIA to implement this Transition Plan

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
None

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Classified or Sensitive Information that is not releasable to the public is included in the Transition Plan. | Include if applicable.

## I. Additional Information
FTI Program Office proposes a FTI Last Mile Microwave solution using commercial spectrum to provide telecommunications diversity for the JOL ARSR. The FTI Last Mile Microwave solution will replace the FAA 2GHz LDRCL system currently in place. It is estimated that, once funded, implementation will take approximately 12 months before the FAA LDRCL would be decommissioned. The system is paired with FAA 922572/ M1828.