## A. Title Page
National Aeronautics and Space Administration (NASA) Transition Plan for the 1755-1780 MHz Band
| Primary Point of Contact: John E Zuzek Office: Spectrum Policy and Planning Telephone Number: 216-433-3469 E-mail: jezuzek@nasa.gov |  | Alternate Point of Contact: Bradford A. Kaufman Office: SCaN/Spectrum Policy and Planning Telephone Number: 202-358-0767 E-mail: bkaufman@nasa.gov
Certification regarding Classified and Sensitive Information: I, Victor D. Sparrow, certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information. As applicable: A separate Annex containing a complete transition plan including all classified and sensitive data is provided under separate cover via authorized channels.

## B. General Information
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs: | 0.572 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 0
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 0.547
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | No
4 | a. Name of Responsible Officer: Victor D. Sparrow
b. (Optional) Office:
c. (Optional) Telephone Number:
d. (Optional) E-mail:
5 | Total Transition Plan Cost ($M): | 1.537

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment (MHz) | Transition Timeline (Months)
NASA940130 | 1780.5 |  | 25 | 29.7 | LARC | Telemetry | LaRC Research Aircraft | NC, VA, MD, DE | VA | 370507N | 0762244W | US | AIR | AIR | Vacate NO Temp | 4400-4940 | 21 | Microwave
TRR
ACTS
[18 empty] | PGM | Indefinite
[18 empty] | Video | Vacate with Temp
[18 empty] | TT&C | Vacate NO Temp
Telemetry
Robotics
UAS
Other

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
NASA940130 | NASA, VA, MD, DE | N/A | N/A | 21

## E. Timeline for Funds
System Name | System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
LaRC Research Aircraft | LARC | 0.025 | 0 | 0 | 0.84 | 0.125 | 0.99 | 6 | 18 |  |  | Re-engineeriung of system to different frequency band and purchase of new equipment
Alternate Band Engineeting Studies | HQ | 0.547 | 0 | 0.547 | 0 | 0 | 0.547 | 1 | 1 |  |  | Analysis of 2015-2110 MHz and 2200-2290 MHz bands for relocation of federal systems from 1755-1850 MHz.

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Classified or Sensitive Information that is not releasable to the public is included in the Transition Plan. | Not applicable.
2