## A. Title Page
Department of the Treasury (Treasury) Transition Plan for the 1755-1780 MHz Band
Alternate Point of Contact: Albert Rolek Office: Treasury Inspector General for Tax Administration Telephone Number: 215-861-1026 E-mail: al.rolek@tigta.treas.gov
Primary Point of Contact: Ralph Robles Office: Treasury Inspector General for Tax Administration Telephone Number: 202-285-7980 E-mail:ralph.robles@tigta.treas.gov
Alternate Point of Contact: Thomas W. Birmingham, Jr. Office: Internal Revenue Service - Criminal Investigation Telephone Number: 202-317-6641 E-mail: thomas.birmingham@ci.irs.gov
Certification regarding Classified and Sensitive Information: I, Ralph Robles, certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information. A separate Annex containing a complete transition plan including all classified and sensitive data is provided under separate cover via authorized channels. [As applicable: A separate Annex containing a complete transition plan including all classified and sensitive data is provided under separate cover via authorized channels.]

## B. General Information
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs: | 0 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 0
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 0
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | No
4 | a. Name of Responsible Officer: | Ralph Robles
| b. (Optional) Office: | TIGTA/TFSD
| c. (Optional) Telephone Number: | 202-285-7980
| d. (Optional) E-mail: | ralph.robles@tigta.treas.gov
5 | Total Transition Plan Cost ($M): | 7.801

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment | Transition Timeline (Months)
T 060040 | 1760 MHz |  | 6 | 6 | IRS-CI | Video | CI TECHOPS | USP | USP | XXXXXXN | XXXXXXXW | USP | XXXXXXN | XXXXXXXW | Vacate NO Temp | 2200 - 2290 MHz | 12 | Microwave
T 020185 | 1765 MHz |  | 6 | 6 | TIGTA | Video | TIGTA TECHOPS | USP | USP | XXXXXXN | XXXXXXXW | USP | XXXXXXN | XXXXXXXW | Vacate NO Temp | 2200 - 2290 MHz | 12 | TRR
ACTS
[18 empty] | PGM | Indefinite
[18 empty] | Video | Vacate with Temp
[18 empty] | TT&C | Vacate NO Temp
Telemetry
Robotics
UAS
Other

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
T 060040 | USP | NOT APPLICABLE | NOT APPLICABLE | Within 12 months
T 020185 | USP | NOT APPLICABLE | NOT APPLICABLE | Within 12 months

## E. Timeline for Funds
System Name | System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
CI TECHOPS | IRS-CI | 0 | 0 | 0 | 6.521 | 1.04 | 7.561 | 6 | 60 | 0 | N/A | Funds required to replace antiquated, analog equipment. The equipment is channelized so is still useable. However, the lost of one frequency cuts down the number of available channels by 33% (1 of 3 available) which diminishes efforts to avoid interference in this very congested band. Procurement of spectrally efficient COFDM equipment will help avoid interference when encountered.
TIGTA TECHOPS | TIGTA | 0 | 0 | 0 | 0.1125 | 0.1275 | 0.24 | 6 | 12 | 0 | N/A | Procurement of replacement digital COFDM microwave equipment and IP-based systems which are more spectrally efficient than the current wideband analog equipment.

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1 | In order to execute this plan, it is necessary for NTIA to assign fequencies to IRS-CI in the 2.2 to 2.29 GHz range. IRS-CI currently does not have any frequencies in the S band. IRS-CI will be transistioning its existing L band equipment into more spectrally efficient digital COFDM frequecies in the S Band. Commercial services may no longer be a viable option for most operations due to the removal of the unlimited data plans for federal users. Commercial services may continue to be used on a limited basis for very short-term operations. The majority of the transition plan will rely on vacating the L band and switching to the S Band.

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
NONE

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Classified or Sensitive Information that is not releasable to the public is included in the Transition Plan. | Not Applicable.
2 | Obtaining Replacement Frequncies | Additional frequencies is requested in the S Band (2.2 - 2.29 GHz) to replace the loss of these frequencies.
3 | Availability of Equipment | Potential delays could occur if there was a lack of available replacment equipment.

## I. Additional Information
Although both TIGTA and IRS – CI believe they will be able to vacate the affected frequencies within 12 months of receipt of funding, they both believe it will take up to 5 years (60 months) to reach comparable capability. The reason for this extended time is because the small disguised video transmitter equipment is currently not available and to allow for futher advancement in the microwave arena.